## Trainings concept
Trainings concept for specialists at the regional and local levels of SSUFSCP on official controls concerning compliance with legislation on the animal welfare of farmed animals during keeping, transport and killing
Aim of the concept: - to create a training system for specialists at the regional and local levels of the State Service of Ukraine on Food Safety and Consumer Protection (SSUFSCP) to ensure a uniform approach to carrying out official controls to check the compliance by business operators with legislation on the welfare of farmed animals during keeping, transport and killing
Target audience: - specialists at the regional level of the SSUFSCP - 150 people; - specialists at the local level of the SSUFCSP (official/authorised veterinarians who carry out certain official control measures concerning compliance with animal welfare legislation) - 707 people;
Important note: The concept does not apply to pets, stray animals, zoo animals, or horses (intended for use during entertainment, cultural, and/or sports events and activities, or exclusively for food production) and other animals used for scientific or educational purposes. It is aimed at inspectors of the State Service of Ukraine on Food Safety and Consumer Protection who carry out official controls on the welfare of farm animals.
Implementation: The trainings will be conducted by trained national trainers (16 specialists at the central and regional levels, of which 8 are trainers control for keeping, 2 are trainers for control f transport, 4 are trainers for control of slaughter, and 2 are trainers for border control) under the coordination of the central office of the SSUFSCP and with the technical support of international technical assistance projects and other involved organizations. Trainings for specialists at the regional and local levels of the SSUFSCP will be conducted in three phases: - theoretical: trained trainers will conduct online trainings for regional and local specialists; - practical: trained trainers will conduct simulated inspections for regional specialists; - local: trained regional specialists will conduct simulated inspections for local specialists. The stages are described in more detail below. All materials from the online trainings and video materials from the simulated inspections will be used to design a series of distance learning courses "Official control over compliance with legislation on the animal welfare of farmed animals during keeping, transport and killing" (the draft structure of the course is provided on the third sheet of this document), which will be available on the SSUFSCP distance learning platform for all specialists who were unable to participate in the trainings or who have just started working. This means that such specialists will be able to complete the theoretical training remotely, and trained trainers will be able to conduct practical simulated inspections as needed.
Phase І. Theoretical: online trainings
Prior to the practical stage, a series of online trainings will be conducted to provide theoretical knowledge. Each online training will be recorded. All videos, together with the training materials, will be combined into several distance learning courses on "Official control for compliance with legislation on the welfare of farmed animals during keeping, transport, and killing," which will be uploaded to the SSUFSCP's distance learning platform. Only specialists who have participated in the online training and received certificates of successful completion will be admitted to the subsequent practical stage.
Training name | Aim | Content (of the presentation) | Comments | Supported by | Format and venue | Number of participants | Estimated duration | Dates
Introduction to basic knowledge for animal welfare of farmed animals and the purpose of implementing EU animal welfare rules for farmed animals in Ukraine | 1) familiarisation with basic knowledge of farmed animal welfare in accordance with international standards and EU animal welfare rules; 2) clarification of the purpose of implementing EU farmed animal welfare rules in Ukraine; 3) familiarisation with the harmonised national legislation on farmed animal welfare. | 1. Presentation of the training concept for specialists at the regional and local levels of the SSUFSCP to ensure a uniform approach to carrying out official controls for compliance by business operators with legislation on the welfare of farmed animals during keeping, transport and killing. 2. Basic knowledge of farmed animal's welfare in accordance with the World Organisation for Animal Health (WOAH) and EU regulations. 3. The legislative framework of Ukraine on farmed animal's welfare. | 1. The training concept must be presented by a representative of the SSUFSCP or a QFTP expert to familiarise participants with how the training process will take place. 2. The speaker can be a representative of the Ministry of Economy, and the content of the presentation will depend on the timing of the training, as the Ministry of Economy is actively working on the legislative harmonisation process. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | QFTP/ILCA ІІ | online, Zoom platform | up to 150 | 4 days for 4 hours | April 2025
Keeping of farmed animals
General requirements for the welfare of farmed animals, cattle and calves during keeping | 1) familiarisation with the requirements of national legislation on farmed animal's welfare during keeping; 2) explanation of the requirements for the welfare of cattle and calves during their keeping; 3) presentation of international experience in the practical implementation of EU rules on the welfare of cattle and calves during their keeping; 4) highlighting the principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of cattle and calves during keeping. | 1. Requirements for the welfare of farmed animals during keeping, as approved by the Order of the Ministry of Economic Development, Trade and Agriculture of Ukraine dated 08.02.2021 No. 224: - general requirements for all species of farmed animals; - specific requirements for the welfare of cattle and calves. 2. International experience in ensuring the welfare of cattle and calves during their keeping. 3. Principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of cattle and calves during their keeping. | The presentation No2 will be delivered by an international expert, who will use practical examples to demonstrate how legislative requirements for animal welfare are implemented by business operators on-farm. The objective of presentation No3 is to demonstrate how an official inspector should verify legislative welfare requirements in practice, i.e., how they must ensure that animals have sufficient space, feed, water, etc. This session will serve as the theoretical preparation before the practical stage, where participants will engage in simulated inspections and utilise the approved checklists. Test questions must be prepared and pre- and post-event testing will be conducted. A question and answer session will also be held. | QFTP | online, Zoom platform | up to 850 | 2 days (for 4 hours) | November-December 2025
Requirements for the welfare of small ruminants during keeping | 1) explanation of the requirements for the welfare of small ruminants during their keeping; 2) presentation of international experience in the practical implementation of EU rules on the welfare of small ruminants during their keeping; 3) highlighting the principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of small ruminants during keeping. | 1) Specific requirements for the welfare of small ruminants during keeping in accordance with the Order of the Ministry of Economic Development, Trade and Agriculture of Ukraine dated 08.02.2021 No. 224. 2) International experience in ensuring the welfare of small ruminants during keeping. 3) Principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of small ruminants during their keeping. | same comments as in D9 | QFTP | online, Zoom platform | up to 850 | 2 days (for 4 hours) | November-December 2025
Requirements for the welfare of broilers during keeping | 1) explanation of the requirements for the welfare of broilers during keeping; 2) presentation of international experience in the practical implementation of EU rules on the welfare of broilers during keeping; 3) highlighting the principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of broilers during keeping. | 1) Specific requirements for the welfare of broilers during keeping in accordance with the Order of the Ministry of Economic Development, Trade and Agriculture of Ukraine dated 08.02.2021 No. 224. 2) International experience in ensuring the welfare of broilers during keeping. 3) Principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of broilers during their keeping | same comments as in D9 | to be decided | online, Zoom platform | up to 850 | 2 days (for 4 hours) | November-December 2025
Requirements for the welfare of laying hens during keeping | 1) explanation of the requirements for the welfare of laying hens during keeping; 2) presentation of international experience in the practical implementation of EU rules on the welfare of laying hens during keeping; 3) highlighting the principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of laying hens during keeping. | 1) Specific requirements for the welfare of laying hens during keeping in accordance with the Order of the Ministry of Economic Development, Trade and Agriculture of Ukraine dated 08.02.2021 No. 224. 2) International experience in ensuring the welfare of laying hens during keeping. 3) Principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of laying hens during their keeping. | same comments as in D9 | to be decided | online, Zoom platform | up to 850 | 2 days (for 4 hours) | November-December 2025
Requirements for the welfare of pigs during keeping | 1) explanation of the requirements for the welfare of pigs during keeping; 2) presentation of international experience in the practical implementation of EU rules on the welfare of pigs during keeping; 3) highlighting the principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of pigs during keeping. | 1) Specific requirements for the welfare of pigs during keeping in accordance with the Order of the Ministry of Economic Development, Trade and Agriculture of Ukraine dated 08.02.2021 No. 224. 2) International experience in ensuring the welfare of pigs during keeping. 3) Principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of pigs during their keeping | same comments as in D9 | to be decided | online, Zoom platform | up to 850 | 2 days (for 4 hours) | November-December 2025
Requirements for the welfare of working horses (Equidae) | 1) clarification of the minimum requirements for ensuring the welfare of working equidae (Equidae), namely horses, donkeys, mules and hinnies, whose tractive power is used by their owners/keepers in transport and agricultural work; 2) presentation of international experience in the practical implementation of EU rules on the welfare of working equidae (Equidae); 3) highlighting the principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of working equidae (Equidae). | 1) Specific requirements for the welfare of working horses (Equidae) during keeping in accordance with the Order of the Ministry of Economy dated 29.07.2024 No. 2266. 2) International experience in ensuring the welfare of working horses (Equidae) during keeping. 3) Principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of working horses (Equidae) during their keeping | same comments as in D9 | to be decided | online, Zoom platform | up to 850 | 2 days (for 4 hours) | November-December 2025
Transport of farmed animals
General requirements for the animal welfare during transport and special transport of different farmed animal species by land transport | 1) detailed clarification of the requirements for the welfare of farm animals during their transport by land; 2) presentation of international experience in the practical implementation of EU rules on the welfare of farmed animals during their transport by land; 3) highlighting the main principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of farm animals during their transport by land. | The content will be agreed after the approval of the national by-law equivalent to EU legislation. |  | QFTP/to be decided | online, Zoom platform | up to 850 | 2 days (for 4 hours) | June 2026
General requirements for the animal welfare during transport and special transport of different farmed animal species by water transport | 1) detailed clarification of the requirements for the welfare of farm animals during their transport by water; 2) presentation of international experience in the practical implementation of EU rules on the welfare of farmed animals during their transport by water; 3) highlighting the main principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of farm animals during their transport by water. | The content will be agreed after the approval of the national by-law equivalent to EU legislation. |  | QFTP/to be decided | online, Zoom platform | up tp 850 | 2 days (for 4 hours) | June 2026
General requirements for the animal welfare during transport and special transport of different farmed animal species by air transport | 1) detailed clarification of the requirements for the welfare of farm animals during their transport by air; 2) presentation of international experience in the practical implementation of EU rules on the welfare of farmed animals during their transport by air; 3) highlighting the main principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of farm animals during their transport by air. | The content will be agreed after the approval of the national by-law equivalent to EU legislation. |  | QFTP/to be decided | online, Zoom platform | up to 850 | 2 days (for 4 hours) | June 2026
Killing of farmed animals
General requirements for ensuring the welfare of farmed animals at the time of killing and related operations | familiarisation with the requirements of national legislation on the welfare of farm animals at the time of killing and related operations. | 1. General requirements for ensuring the animal welfare at the time of killing and related operations in accordance with the Order of the Ministry of Economy dated 29.08.2022 No. 628: - equipment for restraining and stunning animals; - stunning methods; - checks on the effectiveness of stunning; - standard operating procedures; - personnel requirements. 2) Requirements for slaughterhouses in accordance with the Order of the Ministry of Economy dated 29.08.2022 No. 628: - planning, construction, and equipment of slaughterhouses; - operational rules for slaughterhouses. 3. Requirements for the depopulation and forced killing of animals in accordance with the Order of the Ministry of Economy dated 29.08.2022 No. 628. | This presentation was prepared as part of the QFTP activities. A responsible project needs to be identified for the preparation of presentations Nos 2 and 3. | QFTP/to be decided | online, Zoom platform | up to 850 | 2 days (for 4 hours) | February 2026
Specifics of the slaughter of ruminants for their welfare | 1) clarification of the requirements for the welfare of ruminants at the time of their slaughter; 2) presentation of international experience in the practical implementation of EU rules on the welfare of ruminants at the time of their slaughter; 3) highlighting the principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of ruminants at the time of their slaughter. | 1. Specific requirements for the welfare of ruminants at the time of slaughter in accordance with the Order of the Ministry of Agrarian Policy and Food of Ukraine dated 29.08.2022 No. 628. 2. International experience in ensuring the welfare of ruminants at the time of slaughter. 3. Principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of ruminants at the time of slaughter. | Presentation No2 will be delivered by an international expert, who will use practical examples to demonstrate how legislative requirements are implemented in slaughterhouses. The objective of presentation No3 is to demonstrate how an official inspector should verify legislative requirements for the welfare of ruminants at the time of killing. This will serve as the theoretical preparation before the practical stage, where participants will engage in simulated inspections and use the approved checklists. It is necessary to prepare test questions and conduct a pre- and post-event testing. A question and answer session will also be held. | QFTP | online, Zoom platform | up to 850 | 2 days (for 4 hours) | February 2026
Specifics of the slaughter of poultry for their welfare | 1) clarification of the requirements for the welfare of poultry at the time of their slaughter; 2) presentation of international experience in the practical implementation of EU rules on the welfare of poultry at the time of their slaughter; 3) highlighting the principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of poultry at the time of their slaughter. | 1. Specific requirements for the welfare of poultry at the time of slaughter in accordance with the Order of the Ministry of Economy dated 29.08.2022 No. 628. 2. International experience in ensuring the welfare of poultry at the time of slaughter. 3. Principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of poultry at the time of their slaughter. | same comments as in D20 | to be decided | online, Zoom platform | up to 850 | 2 days (for 4 hours) | March 2026
Specifics of the slaughter of pigs for their welfare | 1) clarification of the requirements for the welfare of pigs at the time of their slaughter; 2) presentation of international experience in the practical implementation of EU rules on the welfare of pigs at the time of their slaughter; 3) highlighting the principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of pigs at the time of their slaughter. | 1. Specific requirements for the welfare of pigs at the time of slaughter in accordance with the Order of the Ministry of Economy dated 29.08.2022 No. 628. 2. International experience in ensuring the welfare of pigs at the time of slaughter. 3. Principles of carrying out inspections concerning compliance by business operators with legislation on the welfare of pigs at the time of slaughter. | same comments as in D20 | to be decided | online, Zoom platform | up to 850 | 2 days (for 4 hours) | March 2026
Етап ІІ. Practical: Conducting simulated trainings for regional specialists
For the practical training of regional specialists of the SSUFSCP and for knowledge exchange, trained trainers will conduct simulated inspections in the regions according to the business operators' activities (handling, transport, and killing of animals) and types of animals (ruminants, poultry, pigs), during which trainers will demonstrate the stages of preparation for an inspection and the performance of the inspection. When planning such simulated inspections, the following should be considered: - in one region, there may be no poultry farms that keep broilers, and in another, no slaughterhouses for pigs. Therefore, if several regions are combined in one event dedicated to keeping broilers, specialists from regions with broiler farms should be invited; - after returning to their regions, participants must conduct local simulated inspections for the remaining SSUFSCP specialists in the region (e.g., district specialists) who carry out animal welfare control measures. For theoretical preparation before a simulated inspection, all participants must attend all online trainings and receive certificates of successful completion before the simulated inspection begins. Upon completion of a simulated inspection, participants will be tasked with completing a report on the results of the planned (unplanned) official control (inspection) regarding compliance by business operators with animal welfare legislation, drawing up a list of non-compliances, and proposing possible corrective measures to eliminate the non-compliances. After the simulated inspection, the trainer and the group will prepare a report on the results of the simulated inspection. The report must contain information on: - the main inspection results, including any non-compliances identified; - recommendations to the business operator regarding the necessary corrective measures (if non-compliances are identified); - challenges and lessons learned during the inspection. During each training, practical simulated inspections must be recorded on video. All video recordings will be added to the distance learning courses "Official control for compliance with legislation on the welfare of farmed animals during keeping, transport, and killing," which will then be available on the SSUFSCP's distance learning platform for all SSUFSCP specialists.
Training name | Aim | Content (of the presentation) | Comments | Responsible/ Supported by | Format and venue | Number of participants | Estimated duration | Dates
Handling of farmed animals
Official control (inspection) regarding compliance by business operators with legislation on the welfare of ruminants and calves during keeping | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the animal welfare during the keeping of cattle and calves; 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who keep cattle and calves; 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who keep cattle and calves during a simulated inspection. | 1. Theoretical part: the content will be determined after the approval of checklists and guidelines/SOPs. 2. Practical part: a on-site visit to conduct a simulated inspection of a business operator who keeps cattle and calves. | Five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of QFTP | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 2 days | March 2026/March 2027
Official control (inspection) regarding compliance by business operators with legislation on the welfare of small ruminants during keeping | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the animal welfare during the keeping of small ruminants; 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who keep small ruminants; 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who keep small ruminants during a simulated inspection. | 1. Theoretical part: the content will be determined after the approval of checklists and guidelines/SOPs. 2. Practical part: a on-site visit to conduct a simulated inspection of a business operator who keeps small ruminants. | Five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of QFTP | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 2 days | March 2026/March 2027
Official control (inspection) regarding compliance by business operators with legislation on the welfare of broilers during keeping | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the animal welfare during the keeping of broilers; 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who keep broilers; 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who keep broilers during a simulated inspection. | 1. Theoretical part: the content will be determined after the approval of checklists and guidelines/SOPs. 2. Practical part: a on-site visit to conduct a simulated inspection of a business operator who keeps broilers. | Five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of "TBC" | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 2 days | April 2026/April 2027
Official control (inspection) regarding compliance by business operators with legislation on the welfare of laying hens during keeping | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the animal welfare during the keeping of laying hens; 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who keep laying hens; 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who keep laying hens during a simulated inspection. | 1. Theoretical part: the content will be determined after the approval of checklists and guidelines/SOPs. 2. Practical part: a on-site visit to conduct a simulated inspection of a business operator who keeps laying hens. | Five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of "TBC" | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 2 days | May 2026/May 2027
Official control (inspection) regarding compliance by business operators with legislation on the welfare of pigs during keeping | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the animal welfare during the keeping of pigs; 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who keep pigs; 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who keep pigs during a simulated inspection. | 1. Theoretical part: the content will be determined after the approval of checklists and guidelines/SOPs. 2. Practical part: a on-site visit to conduct a simulated inspection of a business operator who keeps pigs. | Five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of "TBC" | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 2 days | June 2026/June 2027
Official control (inspection) regarding compliance by business operators with legislation on the welfare of working horses (Equidae) during keeping | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the welfare of working equidae (Equidae); 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who keep working equidae (Equidae); 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who keep working equidae (Equidae) during a simulated inspection. | 1. Theoretical part: the content will be determined after the approval of checklists and guidelines/SOPs. 2. Practical part: a on-site visit to conduct a simulated inspection of a business operator who keeps working horses (Equidae) | Five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of "TBC" | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 2 days | June 2026/June 2027
Transport of farmed animals
Official control (inspection) regarding compliance by business operators with legislation on the animal welfare of ruminants during land transportation | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the welfare of animals during the transport of ruminants by land; 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who transport ruminants by land; 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who transport ruminants by land during a simulated inspection. | Theoretical part: the content will be determined after the approval of by-laws, checklists and guidelines/SOPs. Practical part: a field visit to conduct a simulated inspection of a business operator who transports ruminants by land. | Five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of QFTP | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 2 days | September 2026/September 2027
Official control (inspection) regarding compliance by business operators with legislation on the animal welfare of poultry during land transportation | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the welfare of animals during the transport of ruminants by land; 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who transport ruminants by land; 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who transport ruminants by land during a simulated inspection. | Theoretical part: the content will be determined after the approval of by-laws, checklists and guidelines/SOPs. Practical part: a field visit to conduct a simulated inspection of a business operator who transports poultry by land. | Five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of "TBC" | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 2 days | October 2026/October 2027
Official control (inspection) regarding compliance by business operators with legislation on the animal welfare of pigs during land transportation | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the welfare of animals during the transport of pigs by land; 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who transport pigs by land; 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who transport pigs by land during a simulated inspection. | Theoretical part: the content will be determined after the approval of by-laws, checklists and guidelines/SOPs. Practical part: a field visit to conduct a simulated inspection of a business operator who transports pigs by land. | Five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of "TBC" | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 2 days | November 2026/November 2027
Official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animal during water and air transportation | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the welfare of farmed animals during their transport by water and air; 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who transport farm animals by water and air; 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who transport farm animals by water and air during a simulated inspection. | Theoretical part: the content will be determined after the approval of by-laws, checklists and guidelines/SOPs. Practical part: a field visit to conduct a simulated inspection of business operators who transport farm animals by water and air. | This training will be conducted if it is relevant and necessary (the decision on this must be made by the SSUFSCP). If necessary, five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of "TBC" | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 2 days | December 2026/December 2027
Killing of farmed animals
Official control (inspection) regarding compliance by business operators with legislation on the welfare of ruminants during slaughter | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the welfare of ruminants at the time of slaughter; 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who slaughter ruminants; 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who slaughter ruminants during a simulated inspection. | Theoretical part: the content will be determined after the approval of checklists and guidelines/SOPs. Practical part: a field visit to conduct a simulated inspection of a business operator who slaughters ruminants. | Five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. The training must include requirements for both large and small slaughterhouses. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of QFTP | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 3 days | April 2026/April 2027
Official control (inspection) regarding compliance by business operators with legislation on the welfare of poultry during slaughter | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the welfare of animals at the time of slaughter of poultry; 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who slaughter poultry; 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who slaughter poultry during a simulated inspection. | Theoretical part: the content will be determined after the approval of checklists and guidelines/SOPs. Practical part: a field visit to conduct a simulated inspection of a business operator who slaughters poultry. | Five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. The training must include requirements for both large and small slaughterhouses. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of "TBC" | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 3 days | May 2026/May 2027
Official control (inspection) regarding compliance by business operators with legislation on the welfare of pigs during slaughter | 1) clarification and working through the procedure for determining the frequency of official controls regarding compliance by business operators with legislation on the welfare of pigs at the time of slaughter; 2) presentation of the approved checklists, SOPs/guidelines for carrying out inspections of business operators who slaughter pigs; 3) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who slaughter pigs during a simulated inspection. | Theoretical part: the content will be determined after the approval of checklists and guidelines/SOPs. Practical part: a field visit to conduct a simulated inspection of a business operator who slaughters pigs. | Five inter-regional events will be held, which means specialists from five regions (5 people from each region) will be invited to one event. The training must include requirements for both large and small slaughterhouses. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in regions under support of "TBC" | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 3 days | June 2026/June 2027
Phase IIІ. Local: conducting simulated inspections by trained regional specialists
For the practical training of local SSUFSCP specialists and for knowledge exchange, the regional specialists, who were trained during the previous phase, will conduct simulated inspections in each region for local specialists according to the business operators' activities (keeping, transport, and killing of animals) and types of animals (ruminants, poultry, pigs and, if necessary, rabbits and fur animals), during which they will demonstrate the stages of preparation for an inspection and the performance of the inspection. National welfare trainers may join these trainings to observe the trained regional specialists regarding their level of knowledge gained in the previous phase and the correctness of knowledge transfer to local specialists. Such simulated inspections can be held in each district or several districts can be involved in one event. This decision must be made by the SSUFSCP. When planning such simulated inspections, it should be considered that in one district, there may be no poultry farms that keep broilers, and in another, no slaughter points for pigs. Therefore, in case of combining several districts into one event dedicated to keeping broilers, specialists from districts with poultry farms should be invited. An example is provided below. Thus, the final list of simulated inspections in the regions for local specialists will be formed by the territorial body of the SSUFSCP separately for each region after the second phase. After the list of district simulated inspections for each region is formed and the timing of their conduct is determined, this information will be transferred to the training calendar on the next page of this document. For theoretical preparation for a simulated inspection, all participants, before the start of the simulated inspection, must attend all online trainings and receive a certificate or complete the distance learning courses "Official control for compliance with legislation on the welfare of farmed animals during keeping, transport, and killing" and receive certificates of their successful completion. Upon completion of a simulated inspection, participants will be tasked with filling out a report on the results of the planned (unplanned) official control (inspection) regarding compliance by business operators with animal welfare legislation, forming a list of non-compliances and proposing possible corrective measures to eliminate the non-compliances. After the simulated inspection, the trainer prepares a report on the results of such a simulated inspection. The report must contain information on: - the number and names of participants; - the main inspection results, including any non-compliances identified; - recommendations to the business operator regarding the necessary corrective measures (if non-compliances are identified); - challenges and lessons learned during the inspection.
Name | Aim | Content (of the presentation) | Comments | Responsible | Format and venue | Number of participants | Estimaed duration | Dates
Handling of farmed animals
EXAMPLE Simulated inspection of business operators who keep cattle and calves regarding compliance with animal welfare legislation | 1) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who keep cattle and calves during a simulated inspection. | Practical part: a field visit to conduct a simulated inspection of a business operator who keeps cattle and calves. | Specialists from Bila Tserkva, Rokytne, and Fastiv districts of Kyiv region will be invited (5 people from each district). It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in Kyiv region | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 1 day
EXAMPLE Simulated inspection of business operators who keep broilers regarding compliance with animal welfare legislation | 1) practical application of checklists, SOPs/guidelines and working through the principles of inspecting business operators who keep broilers during a simulated inspection. | Practical part: a field visit to conduct a simulated inspection of a business operator who keeps broilers. | Specialists from Myronivka district of Kyiv region will be invited. It is necessary to prepare test questions and conduct a test at the beginning and end of the event. A question and answer session will also be held. | Main administration of SSUFSCP in Kyiv region | on-site, venue will be decided | no more than 25 (participants will be divided into two groups for effective work) | 1 day
… | … | … | … | … | … | … | …
Transport of farmed animals
… | … | … | … | … | … | … | …
Killing
… | … | … | … | … | … | … | …

## Calendar planning for trainings
Training name | 2025 | [11 empty] | 2026 | [11 empty] | 2027
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
Phase І. Theoretical: online trainings
Introduction to basic knowledge for animal welfare of farmed animals and the purpose of implementing EU animal welfare rules for farmed animals in Ukraine | bar: Apr
Keeping of farmed animals
General requirements for the welfare of farmed animals, cattle and calves during keeping | bar: Nov to Dec
Requirements for the welfare of small ruminants during keeping | bar: Nov to Dec
Requirements for the welfare of broilers during keeping | bar: Nov to Dec
Requirements for the welfare of laying hens during keeping | bar: Nov to Dec
Requirements for the welfare of pigs during keeping | bar: Nov to Dec
Requirements for the welfare of working horses (Equidae) | bar: Nov to Dec
Transport of farmed animals
General requirements for the animal welfare during transport and special transport of different farmed animal species by land transport | bar: June
General requirements for the animal welfare during transport and special transport of different farmed animal species by water transport | bar: June
General requirements for the animal welfare during transport and special transport of different farmed animal species by air transport | bar: June
Killing of farmed animals
General requirements for ensuring the welfare of farmed animals at the time of killing and related operations | bar: Feb
Specifics of the slaughter of ruminants for their welfare | bar: Feb
Specifics of the slaughter of poultry for their welfare | bar: Mar
Specifics of the slaughter of pigs for their welfare | bar: Mar
Phase ІІ. Practical: Conducting simulated trainings for regional specialists
Keeping of farmed animals
Official control (inspection) regarding compliance by business operators with legislation on the welfare of ruminants and calves during keeping | bar: Mar; Mar
Official control (inspection) regarding compliance by business operators with legislation on the welfare of small ruminants during keeping | bar: Mar; Mar
Official control (inspection) regarding compliance by business operators with legislation on the welfare of broilers during keeping | bar: Apr; Apr
Official control (inspection) regarding compliance by business operators with legislation on the welfare of laying hens during keeping | bar: May; May
Official control (inspection) regarding compliance by business operators with legislation on the welfare of pigs during keeping | bar: June; June
Official control (inspection) regarding compliance by business operators with legislation on the welfare of working horses (Equidae) during keeping | bar: June; June
Transport of farmed animals
Official control (inspection) regarding compliance by business operators with legislation on the animal welfare of ruminants during land transportation | bar: Sept; Sept
Official control (inspection) regarding compliance by business operators with legislation on the animal welfare of poultry during land transportation | bar: Oct; Oct
Official control (inspection) regarding compliance by business operators with legislation on the animal welfare of pigs during land transportation | bar: Nov; Nov
Official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animal during water and air transportation | bar: Dec; Dec
Killing of farmed animals
Official control (inspection) regarding compliance by business operators with legislation on the welfare of ruminants during slaughter | bar: Sept; Sept
Official control (inspection) regarding compliance by business operators with legislation on the welfare of poultry during slaughter | bar: Oct; Oct
Official control (inspection) regarding compliance by business operators with legislation on the welfare of pigs during slaughter | bar: Nov; Nov
Phase IIІ. Local: conducting simulated inspections by trained regional specialists
Total number | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Structure of the course
Structure of the distance learning course "Official control for compliance with legislation on the welfare of farmed animals during keeping, transport, and killing"
Aim of the distance learning courses: - to increase the level of skills, knowledge, competencies, and capacities of public sector participants at the individual and organisational levels to carry out official controls (inspections) regarding compliance by business operators with legislation on the welfare of farmed animals during keeping, transport, and killing; - to ensure a uniform approach to carrying out official controls regarding compliance by business operators with legislation on the welfare of farmed animals during keeping, transport, and killing throughout the country.
Target Audience: specialists at the central and regional levels of the SSUFSCP, authorised/official veterinarians who carry out official control measures (inspections) regarding compliance by business operators with legislation on the welfare of farmed animals during keeping, transport, and killing.
Important note: The concept does not apply to pets, stray animals, zoo animals, or horses (intended for use during entertainment, cultural, and/or sports events and activities, or exclusively for food production) and other animals used for scientific or educational purposes. It is aimed at inspectors of the State Service of Ukraine on Food Safety and Consumer Protection who carry out official controls on the welfare of farm animals.
Presentation to introduce the distance learning course "Official control for compliance with legislation on the welfare of farmed animals during keeping, transport, and killing" (aim, target audience, structure, content of modules and lessons, trainers)
Course I. Welfare of farmed animals during their keeping, transport, and killing: an Introduction
Estimated duration of Course I: 2 weeks
Testing prior to completing Course I
Name of lessons | Aims | Content | Technical project responsible for materials | Comments
Introduction with basic knowledge on farm animal welfare and the purpose for introducing EU rules on welfare of farmed animals in Ukraine | 1) Introduction with basic knowledge on farm animal welfare according to international standards and EU rules on animal welfare; 2) Explaining the goal of introducing EU rules on farm animal welfare in Ukraine; 3) Introduction with harmonised national legislation on farm animal welfare. | 1. Video record of the training "Introduction with basic knowledge on welfare of farmed animals and the purpose for introducing EU rules on farm animal welfare in Ukraine"; 2. Training presentations; 3. Additional materials and regulatory/legal documents for introduction. | QFTP
Experience of EU Member States regarding the implementation of official controls on animal welfare during keeping, transport, and killing | 1) Present the European legal framework for official control on animal welfare and the status of harmonisation of Ukrainian legislation in this area; 2) Explain the peculiarities of implementing the official control system on animal welfare in particular EU countries. | 1. Video record of the meeting and report presentation on the experience of EU Member States regarding the implementation of official controls on animal welfare; 2. Report on the experience of EU Member States regarding the implementation of official controls on animal welfare during keeping, transport, and killing. | QFTP
Final test after completing Course I
Course II. Official controls on compliance with welfare of farmed animals legislation during keeping
Estimated duration of Course ІI: 4 weeks
Testing prior to completing Course II
Name of lessons | Aims | Content | Technical project responsible for materials | Comments
General requirements for the welfare of farmed animals (cattle) and calves during keeping | 1) Introduction with the requirements of national legislation on welfare of farmed animals (cattle) during keeping; 2) Explaining the welfare requirements for cattle and calves during keeping; 3) Presentation of international experience in the practical introduction of EU rules regarding cattle welfare and calves welfare during keeping; 4) Explaining the principles of performing inspections regarding business operators' compliance with farm animal welfare legislation during keeping. | 1. Video record of the training "General requirements for the welfare of farmed animals (cattle) and calves during keeping". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | QFTP
Implementation of state control (inspection) regarding compliance by business operators with welfare of rarmed animals legislation during keeping of cattle and calves | 1) Explaining and practicing the procedure for determining the frequency of conducting official control regarding business operators' compliance with legislation on the welfare of farmed animals during the keeping of bovine animals and calves. 2) Presentation of approved checklists, (SOPs)/Instructions for performing the inspection of business operators that keep small animals. 3) Practical application, during simulated inspection, of the checklists, SOPs/Instructions, and practicing the principles of inspecting business operators that keep bovine animals and calves. | 1. Video record of the theoretical part of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animals during the keeping of cattle and calves". 2. Training presentations. 3. Instructions/SOPs. 4. Video record of the simulated inspection of the business operator that keeps cattle and calves. | QFTP
General requirements for the welfare of small ruminants during keeping | 1) Explaining the welfare requirements for small ruminants during keeping. 2) Presentation of international experience in the practical introduction of EU rules regarding the welfare of small ruminants during keeping. 3) Outlining the principles of performing inspections regarding business operators' compliance with legislation on the welfare of small ruminants during keeping | 1. Video record of the training "General requirements for the welfare of small ruminants during keeping". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | QFTP
Implementation of state control (inspection) regarding compliance by business operators with welfare of rarmed animals legislation during keeping of small ruminants | 1) Explaining and practicing the procedure for determining the frequency of conducting official control regarding business operators' compliance with legislation on the welfare of farmed animals during the keeping of small ruminants. 2) Presentation of approved checklists, (SOPs)/Instructions for performing the inspection of business operators that keep small ruminants. 3) Practical application, during simulated inspection, of the checklists, SOPs/Instructions, and practicing the principles of inspecting business operators that keep bovine animals and calves. | 1. Video record of the theoretical part of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animals during the keeping of small ruminants". 2. Training presentations. 3. Instructions/SOPs. 4. Video record of the simulated inspection of the business operator that keeps small ruminants. | QFTP
General requirements for the welfare of broilers during keeping | 1) Explaining the welfare requirements for broilers during their keeping. 2) Presentation of international experience in the practical introduction of EU rules regarding the welfare of broilers during keeping. 3) Outlining the principles of performing inspections regarding business operators' compliance with legislation on the welfare of broilers during keeping | 1. Video record of the training "General requirements for the welfare of broilers during keeping". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | to be decided
Здійснення Implementation of state control (inspection) regarding compliance by business operators with welfare of rarmed animals legislation during keeping of broilers | 1) Explaining and practicing the procedure for determining the frequency of conducting official control regarding business operators' compliance with legislation on the welfare of farmed animals during the keeping of broilers. 2) Presentation of approved checklists, (SOPs)/Instructions for performing the inspection of business operators that keep broilers. 3) Practical application, during simulated inspection, of the checklists, SOPs/Instructions, and practicing the principles of inspecting business operators that keep broilers. | 1. Video record of the theoretical part of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animals during the keeping of broilers". 2. Training presentations. 3. Instructions/SOPs. 4. Video record of the simulated inspection of the business operator that keeps broilers. | to be decided
General requirements for the welfare of laying hens during keeping | 1) Explaining the welfare requirements for laying hens during their keeping. 2) Presentation of international experience in the practical introduction of EU rules regarding the welfare of laying hens during keeping. 3) Outlining the principles of performing inspections regarding business operators' compliance with legislation on the welfare of laying hens during keeping | 1. Video record of the training "General requirements for the welfare of laying hens during keeping". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | to be decided
Implementation of state control (inspection) regarding compliance by business operators with welfare of rarmed animals legislation during keeping of laying hens | 1) Explaining and practicing the procedure for determining the frequency of conducting official control regarding business operators' compliance with legislation on the welfare of farmed animals during the keeping of laying hens. 2) Presentation of approved checklists, (SOPs)/Instructions for performing the inspection of business operators that keep laying hens. 3) Practical application, during simulated inspection, of the checklists, SOPs/Instructions, and practicing the principles of inspecting business operators that keep laying hens. | 1. Video record of the theoretical part of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animals during the keeping of laying hens". 2. Training presentations. 3. Instructions/SOPs. 4. Video record of the simulated inspection of the business operator that keeps laying hens. | to be decided
General requirements for the welfare of pigs during keeping | 1) Explaining the welfare requirements for pigs during keeping. 2) Presentation of international experience in the practical introduction of EU rules regarding the welfare of pigs during keeping. 3) Outlining the principles of performing inspections regarding business operators' compliance with legislation on the welfare of pigs during keeping | 1. Video record of the training "General requirements for the welfare of pigs during keeping". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | to be decided
Implementation of state control (inspection) regarding compliance by business operators with welfare of rarmed animals legislation during keeping of pigs | 1) Explaining and practicing the procedure for determining the frequency of conducting official control regarding business operators' compliance with legislation on the welfare of farmed animals during the keeping of pigs. 2) Presentation of approved checklists, (SOPs)/Instructions for performing the inspection of business operators that keep pigs. 3) Practical application, during simulated inspection, of the checklists, SOPs/Instructions, and practicing the principles of inspecting business operators that keep pigs. | 1. Video record of the theoretical part of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animals during the keeping of pigs". 2. Training presentations. 3. Instructions/SOPs. 4. Video record of the simulated inspection of the business operator that keeps pigs. | to be decided
General requirements for the welfare of working horses (Equidae) during keeping | 1) Explaining the welfare requirements for working horses (Equidae) during keeping. 2) Presentation of international experience in the practical introduction of EU rules regarding the welfare of working horses (Equidae) during keeping. 3) Outlining the principles of performing inspections regarding business operators' compliance with legislation on the welfare of working horses (Equidae) during keeping | 1. Video record of the training "General requirements for the welfare of working horses (Equidae) during keeping". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | to be decided
Implementation of state control (inspection) regarding compliance by business operators with welfare of rarmed animals legislation during keeping of working horses (Equidae) | 1) Explaining and practicing the procedure for determining the frequency of conducting official control regarding business operators' compliance with legislation on the welfare of farmed animals during the keeping of lworking horses (Equidae). 2) Presentation of approved checklists, (SOPs)/Instructions for performing the inspection of business operators that keep working horses (Equidae). 3) Practical application, during simulated inspection, of the checklists, SOPs/Instructions, and practicing the principles of inspecting business operators that keep working horses (Equidae). | 1. Video record of the theoretical part of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animals during the keeping of working horses (Equidae)". 2. Training presentations. 3. Instructions/SOPs. 4. Video record of the simulated inspection of the business operator that keeps working horses (Equidae). | to be decided
Final test after completing Course II
Course III. Official controls on compliance with welfare of farmed animals legislation during transport
Estimated duration of Course ІІI: 4 weeks
Testing prior to completing Course III
General requirements for the welfare of animals during transport and the specifics of transporting different species of farmed animals by road to ensure their welfare | 1) Introduction with the requirements of national legislation on the welfare of farmed animals during their transport. 2) Detailed explanation of the welfare requirements for farmed animals during their transport by road. 3) Presentation of international experience in the practical introduction of eu rules regarding the welfare of farmed animals during their transport by road. 4) Outlining the key principles of performing inspections regarding business operators' compliance with legislation on the welfare of farmed animals during their transport by road. | 1. Video recording of the training "General requirements for the welfare of animals during transport and the specifics of transporting different species of farmed animals by road to ensure their welfare". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | to be decided
Implementation of official control (inspection) regarding compliance by business operators with legislation on animal welfare during the transport of ruminants by road | 1) Explanation and practical application of the procedure for determining the frequency of official control measures regarding the compliance of business operators who transport ruminants by road with animal welfare legislation. 2) Presentation of approved checklists and SOPs/instructions for inspecting business operators who transport ruminants by road. 3) Practical application, during a simulated inspection, of the checklists and SOPs/instructions and practicing the principles of inspecting business operators who transport ruminants by road. | 1. Video recording of the theoretical part of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on animal welfare during the transport of ruminants by road". 2. Training presentations. 3. Instructions/SOPs. 4. Video recording of the simulated inspection of a business operator that transports ruminants by road. | QFTP
Implementation of official control (inspection) regarding compliance by business operators with legislation on animal welfare during the transport of poultry by road | 1) Explanation and practical application of the procedure for determining the frequency of official control measures regarding the compliance of business operators who transport poultry by road with animal welfare legislation. 2) Presentation of approved checklists and SOPs/instructions for inspecting business operators who transport poultry by road. 3) Practical application, during a simulated inspection, of the checklists and SOPs/instructions and practicing the principles of inspecting business operators who transport poultry by road. | 1. Video recording of the theoretical part of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on animal welfare during the transport of poultry by road". 2. Training presentations. 3. Instructions/SOPs. 4. Video recording of the simulated inspection of a business operator that transports ruminants by road. | to be decided
Implementation of official control (inspection) regarding compliance by business operators with legislation on animal welfare during the transport of pigs by road | 1) Explanation and practical application of the procedure for determining the frequency of official control measures regarding the compliance of business operators who transport pigs by road with animal welfare legislation. 2) Presentation of approved checklists and SOPs/instructions for inspecting business operators who transport pigs by road. 3) Practical application, during a simulated inspection, of the checklists and SOPs/instructions and practicing the principles of inspecting business operators who transport pigs by road. | 1. Video recording of the theoretical part of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on animal welfare during the transport of pigs by road". 2. Training presentations. 3. Instructions/SOPs. 4. Video recording of the simulated inspection of a business operator that transports ruminants by road. | to be decided
Specifics of transporting different species of farmed animals by water to ensure their welfare | 1) Explanation and practical application of the procedure for determining the frequency of official control measures regarding the compliance of business operators who transport farmed animals by water with animal welfare legislation. 2) Presentation of approved checklists and SOPs/instructions for inspecting business operators who transport farmed animals by water. 3) Practical application, during a simulated inspection, of the checklists and SOPs/instructions and practicing the principles of inspecting business operators who transport farmed animals by water. | 1. Video recording of the training "Specifics of transporting different species of farmed animals by water to ensure their welfare". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | to be decided
Specifics of transporting different species of farmed animals by air to ensure their welfare | 1) Explanation and practical application of the procedure for determining the frequency of official control measures regarding the compliance of business operators who transport farmed animals by air with animal welfare legislation. 2) Presentation of approved checklists and SOPs/instructions for inspecting business operators who transport farmed animals by air. 3) Practical application, during a simulated inspection, of the checklists and SOPs/instructions and practicing the principles of inspecting business operators who transport farmed animals by air. | 1. Video recording of the training "Specifics of transporting different species of farmed animals by air to ensure their welfare". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | to be decided
Implementation of official control (inspection) regarding compliance by business operators with legislation on animal welfare during the transport of farmed animals by water and air | 1. Explanation and practical application of the procedure for determining the frequency of official control measures (i.e., inspections) regarding the compliance of business operators who transport farmed animals by water and air with animal welfare legislation. 2. Presentation of approved checklists and SOPs/instructions for inspecting business operators who transport farmed animals by water and air. 3. Practical application, during a simulated inspection, of the checklists and SOPs/instructions and practicing the principles of inspecting business operators who transport farmed animals by water and air. | 1. Video recording of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on animal welfare during the transport of farmed animals by water and air". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | to be decided | This lesson will be created if the SSUFSCP decides to conduct this training due to its relevance (or topicality).
Final test after completing Course III
Course IV. Official controls on compliance with welfare of farmed animals legislation during killing
Estimated duration of Course IV: 4 weeks
Testing prior to completing Course IV
General requirements for ensuring the welfare of farmed animals at the time of slaughter and related operations | 1) Introduction with the requirements of national legislation on the welfare of farmed animals at the time of killing and related operations. | 1. Video record of the training "General requirements for ensuring the welfare of farmed animals at the time of killing and related operations". 2. Training presentations. 3. Additional materials and legal documents. | QFTP/to be decided
Specifics of slaughter of ruminants to ensure their welfare | 1) Explaining the welfare requirements for ruminants at the time of slaughter. 2) Presentation of international experience in the practical introduction of EU rules regarding the welfare of ruminants at the time of slaughter. 3) Outlining the principles of performing inspections regarding business operators' compliance with legislation on the welfare of ruminants at the time of their slaughter. | 1. Video of the training "Specifics of slaughter ruminants to ensure their welfare". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | QFTP
Implementation of official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animals at the time of slaughter of ruminants | 1) Explaining and practicing the procedure for determining the frequency of official control regarding business operators' compliance with legislation on the welfare of animals at the time of slaughter of ruminants. 2) Presentation of approved checklists, SOPs/instructions for performing the inspection of business operators that slaughter ruminants. 3) Practical application, during a simulated inspection, of the checklists, SOPs/Instructions, and practicing the principles of inspecting business operators that slaughter ruminants. | 1. Video record of the theoretical part of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animals at the time of slaughter of ruminants". 2. Training presentations. 3. Instructions/SOPs. 4. Video record of the simulated inspection of the business operator that slaughters ruminants. | QFTP
Specifics of slaughter of poultry to ensure their welfare | 1) Explaining the welfare requirements for poultry at the time of slaughter. 2) Presentation of international experience in the practical introduction of EU rules regarding the welfare of poultry at the time of slaughter. 3) Outlining the principles of performing inspections regarding business operators' compliance with legislation on the welfare of poultry at the time of their slaughter. | 1. Video of the training "Specifics of slaughter of poultry to ensure their welfare". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | to be decided
Implementation of official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animals at the time of slaughter of poultry | 1) Explaining and practicing the procedure for determining the frequency of official control regarding business operators' compliance with legislation on the welfare of animals at the time of slaughter of poultry. 2) Presentation of approved checklists, SOPs/instructions for performing the inspection of business operators that slaughter poultry. 3) Practical application, during a simulated inspection, of the checklists, SOPs/Instructions, and practicing the principles of inspecting business operators that slaughter poultry. | 1. Video record of the theoretical part of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animals at the time of slaughter of poultry". 2. Training presentations. 3. Instructions/SOPs. 4. Video record of the simulated inspection of the business operator that slaughters poultry. | to be decided
Specifics of slaughter of pigs to ensure their welfare | 1) Explaining the welfare requirements for pigs at the time of slaughter. 2) Presentation of international experience in the practical introduction of EU rules regarding the welfare of pigs at the time of slaughter. 3) Outlining the principles of performing inspections regarding business operators' compliance with legislation on the welfare of pigs at the time of their slaughter. | 1. Video of the training "Specifics of slaughter of pigs to ensure their welfare". 2. Training presentations. 3. Additional materials and regulatory/legal documents. | to be decided
Implementation of official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animals at the time of slaughter of pigs | 1) Explaining and practicing the procedure for determining the frequency of official control regarding business operators' compliance with legislation on the welfare of animals at the time of slaughter of pigs. 2) Presentation of approved checklists, SOPs/instructions for performing the inspection of business operators that slaughter pigs. 3) Practical application, during a simulated inspection, of the checklists, SOPs/Instructions, and practicing the principles of inspecting business operators that slaughter pigs. | 1. Video record of the theoretical part of the training "Implementation of official control (inspection) regarding compliance by business operators with legislation on the welfare of farmed animals at the time of slaughter of pigs". 2. Training presentations. 3. Instructions/SOPs. 4. Video record of the simulated inspection of the business operator that slaughters pigs. | to be decided
Final test after completing Course IV