## Description
Roadmap for the implementation of EU animal welfare legislation in Ukraine for 2025-2027 (hereinafter - Roadmap)
The purpose of the Roadmap: - is to plan the activities, necessary for the implementation of the EU farm animal welfare legislation during keeping, transport and killing throughout the country; - is to plan the activities, necessary for the implementation of the official control system over the compliance of business operators with the requirements of animal welfare legislation.
Important comment: The Roadmap does not cover the welfare requirements of pets, stray animals, zoo animals, horses (intended for use in entertainment, cultural and/or sporting events) and animals used in scientific research and education.
The Roadmap contains: - a list of activities necessary for the implementation of national legislation on the welfare of farmed animals in accordance with EU legislation, as well as their planning; - a list of activities necessary for the promotion of the farmed animals welfare requirements, as well as their planning are detailed in the annex “Information Campaign Plan”; - a list of activities necessary for the creation and implementation of a system of official control over the compliance of business operators with the requirements of farmed animals welfare, as well as their planning are detailed in the annex “Concept of trainings for specialists of the State Service for Food Safety and Consumer Protection”. In order to implement planned activities in the Roadmap, the responsible authorities - Ministry of Economy, Environment and Agriculture (hereafter - Ministry of Economy) and the State Service for Food Safety and Consumer Protection (hearafter - SSUFSCP), as well as other intrested stakeholders who agree to be involved* have been identified. Each activity has a deadline for the implementation. Any work in relation to activities conducted by interested stakeholders will be done in close communication with the responsible personnel from the Ministry of Economy and the SSUFSCP. This is a “live” document. It is available to all stakeholders taking part in the activities. If necessary, new activities will be added to the Roadmap or changes will be made to the planning. Stakeholders responsible for implementing the activities will enter the status of their implementation.
*List of intrested stakeholders, who agree to be involved: 1) International Technical Assistance Projects (ITA Projects): - Swiss-Ukrainian Programme“Higher Value Added Trade from the Organic and Dairy Sector in Ukrain”(QFTP); - EU project “Further Support in the Improvement of Legislation, Control and Awareness in Animal Health and Welfare, Phytosanitary in Ukraine” (ILCA II); - EU project “Institutional and Policy Reform of Small-Scale Agriculture” (IPRSA II); - EU ERASMUS+ project “Sustainable Livestock Production and Animal Welfare” (SULAWE); - German-Ukrainian project FABU “Promoting the development of vocational education in agricultural colleges of Ukraine” (FABU); 2) Specialised Associations and Business Associations: - Association "Union of Poultry Farmers of Ukraine" (ASPU); - Association of Milk Producers of Ukraine (AVM); - Project "Family Dairy Farms" (SMF); - Association "Pig Farmers of Ukraine" (ASU); - Public Union "Sheep and Goat Breeding of Ukraine" (GS VKU); - Association of Production and Processing Enterprises of the Meat Industry "Meat of Ukraine" (AMU); - European Business Association (EBA); 3) Other organisations: - Food and Agriculture Organisation of the United Nations (FAO); - Embassy of the Kingdom of the Netherlands in Ukraine (EKNU); - Embassy of France in Ukraine (EFU); - National Association of Agricultural Advisory Services of Ukraine (NAADSU); - NGO "Project 1882 Ukraine" (Project 1882); - NGO "Eurogroup for Animals" (EfA); - NGO "Compassion in World Farming" (CIWF).

## Legislation
| Activity | Goal | Description of the approach for implementing the activity | Need for financial resources (yes/no, if yes, indicate source) | Responsible Government Authorities | Stakeholders involved | Deadline | Execution status (yellow - in progress, green - completed)
General activities for the implementation of the EU farm animals welfare requirements during keeping, transport and killing into Ukrainian national legislation
| Screening of compliance of Ukrainian farm animal welfare legislation with EU acquis | Implementation of the requirements of the Association Agreement between Ukraine, of the one hand, and the European Union, the European Atomic Energy Community and their Member States, of the other hand | Conduct an internal screening (adaptation analysis) of existing Ukrainian legislation on animal welfare for compliance with EU acquis, which will help to determine the list of regulatory documents that require amendments or development for full implementation and coverage of EU requirements | No | Ministry of Economy | ILCA II, QFTP | November 2025 | The screening process has been completed. Work plans are being prepared to finalize the alignment of national legislation with EU acquis
| Amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206 in relation to animal welfare | Implementation of by-laws and fulfilling the requirements of the Association Agreement between Ukraine, on the one hand, and the European Union, the European Atomic Energy Community and their Member States, on the other hand | Development of changes necessary for introduction into the Law of Ukraine "On Veterinary Medicine" No. 1206 in the area of animal welfare, taking into account the results of screening | No | Ministry of Economy | - | March, 1, 2026 | A draft Law on Amendments to Certain Laws of Ukraine on Bringing Regulations in the Field of Veterinary Medicine and Animal Welfare into Line with the EU acquis No.12285-d dated 02.05.2025 has been developed and submitted to a committee of the Verkhovna Rada of Ukraine.
| Development of a regulatory framework for maintaining the State Register of documents issued in accordance with animal welfare legislation | There is a need to comply with the requirements of the Law of Ukraine "On Veterinary Medicine" | "Preparation of amendments to the Resolution of the Cabinet of Ministers of Ukraine 'On the approval of the Procedure for maintaining the Register of state certificates confirming sufficient knowledge and skills regarding compliance with animal welfare legislation,' so that, in addition to certificates of knowledge, the Register also contains information on the issuance of temporary permits, vehicle fitness certificates for the transportation of animals, authorizations for short-distance and long-distance journeys, and journey logs | No | Ministry of Economy | ILCA II | March, 1, 2026 | Resolution of the Cabinet of Ministers of Ukraine No. 1520 "On Approval of the Procedure for Maintaining the Register of State Certificates of Sufficient Knowledge and Skills in Compliance with the Requirements of Animal Welfare Legislation" dated 27.12.2024, needs to be revised, in particular, expanding the set of information in the register
| Preparation of the regulatory basis for the implementation of a risk-based system for determining the frequency of state control measures of market operators regarding compliance with the requirements of animal welfare legislation based on the activities of the business operators (keeping/slaughtering/ transportation) | Introduce a risk-based system for determining the frequency of official control measures, as well as prepare annual planning | Analyse the experience of EU countries | No | Ministry of Economy | QFTP | December 2026 | The experience of the Netherlands has been analysed. They determine the frequency of official control measures of business operators whose activities are related to the keeping, slaughtering and transportation of animals based on the results of the inspections and catogarisation of business operators by the degree of risk. Such inspection for categorisation is carried out in accordance with the checklist, which includes animal welfare questions. The darfting of the national procedure has been started.
| Preparation and approval of forms of acts (checklists) drawn up based on the results of planned (and unplanned) state control measures (inspection) regarding compliance by business operators with the requirements of farm animal welfare legislation during keeping, transport and slaughter | Approval of checklists for the implementation of official control measures (inspections) | Preparation of checklists in accordance with approved secondary legislation regarding animal welfare requirements during keeping, transport and slaughter, as well as preparation of act forms and their approval | No | Ministry of Economy | ILCA II/QFTP | March, 1, 2026 | The Ministry of Economy has submitted a draft checklists for the inspection of business operators regarding compliance with the requirements of the farmed animal welfare during keeping, transport and slaughter to the SSUFSCP for finalisation and submission of proposals.
| Updating the order of the Ministry of Agrarian Policy dated 11.10.2024 No. 3933 "On approval of certain regulatory legal acts regarding compliance with the requirements of animal welfare legislation" | There is a need to make changes in accordance with the results of the screening, and in order to bring it into line with the latest amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206 | Preparation and approval of a regulatory document | No | Ministry of Economy | - | January, 1, 2026 | Preparation of draft amendments to the order is underway, which will be approved after the adoption of amendments to the Law of Ukraine on Veterinary Medicine No. 1206
| Preparation and approval of a regulatory document for the implementation of Regulation (EC) 1523/2007 of the European Parliament and of the Council of 11 December 2007 banning the placing on the market and the import or export from the Community of cat and dog fur and products containing such fur | There is a need to bring national legislation into line with EU acquis, fulfilling the requirements of the Association Agreement between Ukraine, on the one hand, and the European Union, the European Atomic Energy Community and their Member States, on the other hand | Preparation and approval of a regulatory document | No | Ministry of Economy | - | March, 1, 2026 | Relevant provisions have been included in the draft amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206.
Activities to implement the EU farm animals welfare requirements during keeping into Ukrainian national legislation
| Amendments to the Order of the Ministry of Economy of Ukraine dated 08.02.2021 No. 224 "On Approval of the Requirements for the Welfare of Farmed Animals During Their Keeping" | There is a need to make changes in accordance with the results of the screening, and in order to bring it into line with the latest amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206 | Development of changes necessary for inclusion in Order No. 224 and their approval | No | Ministry of Economy | ILCA II | March, 1, 2026 | Preparation of draft amendments to the order is underway, which will be approved after the adoption of amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206.
| Preparation and approval of a regulatory document for the implementation of Commission Recommendation (EU) 2016/336 of 8 March 2016 on the application of Council Directive 2008/120/EC laying down minimum standards for the protection of pigs as regards measures to reduce the need for tail docking | There is a need to bring national legislation into line with EU acquis, fulfilling the requirements of the Association Agreement between Ukraine, on the one hand, and the European Union, the European Atomic Energy Community and their Member States, on the other hand | Preparation and approval of a regulatory document | No | Ministry of Economy | - | December 2026 | Draft recommendation has been prepared, which will be approved after the adoption of amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206.
| Ukraine's accession to the Council of Europe Conventions on the Protection of Animals | There is a need to bring national legislation into line with EU acquis, fulfilling the requirements of the Association Agreement between Ukraine, on the one hand, and the European Union, the European Atomic Energy Community and their Member States, on the other hand | Підготовка всіх необхідних документів та співпраця з МЗС для приєднання до Конвенцій | No | Ministry of Economy/Ministry of Foreign Affairs | - | December 2026 | The process of accession to the Conventions has begun
| Revision of the Provisions of the relevant executive authorities in the field of animal welfare | Amendments in accordance with the results of screening and in order to bring them in line with the latest amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206 | Revision of the Provisions, making appropriate changes and their approval | No | Ministry of Economy/SSUFSCP | - | March, 1, 2026 | The process of analysis of the Provisions for compliance with the latest amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206 has begun
Activities to implement the EU farm animals welfare requirements during transport into Ukrainian national legislation
| Preparation and approval of a regulatory document for the implementation of Council Regulation (EC) 1/2005 of 22 December 2004 on the protection of animals during transport and related operations | There is a need to bring national legislation into line with EU acquis, fulfilling the requirements of the Association Agreement between Ukraine, on the one hand, and the European Union, the European Atomic Energy Community and their Member States, on the other hand | Preparation and approval of a regulatory document | No | Ministry of Economy | ILCA II | March, 1, 2026 | Preparation of draft order is underway, which will be approved after the adoption of amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206.
| Regulation (EC) 1255/97 of 25 June 1997 on Community criteria for staging points and amending the route plan referred to in the Annex to Directive 91/628/EEC | There is a need to bring national legislation into line with EU acquis, fulfilling the requirements of the Association Agreement between Ukraine, on the one hand, and the European Union, the European Atomic Energy Community and their Member States, on the other hand | Preparation and approval of a regulatory document | No | Ministry of Economy | ILCA II | March, 1, 2026 | Preparation of draft order is underway, which will be approved after the adoption of amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206.
| Preparation and approval of a regulatory legal document for the implementation of Commission Delegated Regulation (EU) 2023/842 of 17 February 2023 supplementing Regulation (EU) 2017/625 of the European Parliament and of the Council as regards rules on official controls to verify compliance with animal welfare requirements during the transport of animals by livestock vessels | There is a need to bring national legislation into line with EU acquis, fulfilling the requirements of the Association Agreement between Ukraine, on the one hand, and the European Union, the European Atomic Energy Community and their Member States, on the other hand | Preparation and approval of a regulatory document | No | Ministry of Economy | Project 1882 / EfA | March, 1, 2026 | Preparation of draft order is underway, which will be approved after the adoption of amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206.
| Preparation and approval of a regulatory legal document for the implementation of Commission Implementing Regulation (EU) 2023/372 of 17 February 2023 laying down rules on the recording, storage and exchange of written documents of official controls performed on livestock vessels, on contingency plans for livestock vessels in the event of emergencies, on the approval of livestock vessels and on minimum requirements applicable to exit points | There is a need to bring national legislation into line with EU acquis, fulfilling the requirements of the Association Agreement between Ukraine, on the one hand, and the European Union, the European Atomic Energy Community and their Member States, on the other hand | Preparation and approval of a regulatory document | No | Ministry of Economy | Project 1882 / EfA | March, 1, 2026 | Preparation of draft order is underway, which will be approved after the adoption of amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206.
Activities to implement the EU farm animals welfare requirements during killing into Ukrainian national legislation
| Amendments to the Order of the Ministry of Agrarian Policy and Food of Ukraine dated October 11, 2018 No. 628, which approved the Requirements for ensuring the welfare of animals during killing and slaughter | There is a need to make changes in accordance with the results of the screening, and in order to bring it into line with the latest amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206 | Development of changes necessary for inclusion in Order No. 628 and their approval | No | Ministry of Economy | ILCA II | March, 1, 2026 | Preparation of draft amendments to the order is underway, which will be approved after the adoption of amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206.

## legislation-calendar
Activity |  | 2025 | [11 empty] | 2026 | [11 empty] | 2027
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Jan. | Feb. | March | Apr. | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | March | Apr. | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | March | Apr. | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec.
General activities for the implementation of the EU farm animals welfare requirements during keeping, transport and slaughter into Ukrainian national legislation
Screening of compliance of Ukrainian farm animal welfare legislation with EU law | bar: 2025 2 Feb. to 2025 11 Nov.
Amendments to the Law of Ukraine "On Veterinary Medicine" No. 1206 in relation to animal welfare
Development of a regulatory framework for maintaining the State Register of documents issued in accordance with animal welfare legislation
Preparation of the regulatory basis for the implementation of a risk-based system for determining the frequency of state control measures of market operators regarding compliance with the requirements of animal welfare legislation based on the activities of the business operators (keeping/slaughtering/ transportation) | bar: 2025 1 Jan. to 2026 12 Dec.
Preparation and approval of forms of acts drawn up based on the results of planned (and unplanned) state control measures (inspection) regarding compliance by business operators with the requirements of farm animal welfare legislation during keeping, transport and slaughter
Updating the order of the Ministry of Agrarian Policy dated 11.10.2024 No. 3933 "On approval of certain regulatory legal acts regarding compliance with the requirements of animal welfare legislation" | bar: 2025 1 Jan. to 2025 12 Dec.
Preparation and approval of a regulatory document for the implementation of Regulation (EC) 1523/2007 of the European Parliament and of the Council of 11 December 2007 banning the placing on the market and the import or export from the Community of cat and dog fur and products containing such fur
Ukraine's accession to the Council of Europe Conventions on the Protection of Animals | bar: 2025 1 Jan. to 2026 12 Dec.
Revision of the Provisions of the relevant executive authorities in the field of animal welfare
Activities to implement the EU farm animals welfare requirements during keeping into Ukrainian national legislation
Amendments to the Order of the Ministry of Economy of Ukraine dated 08.02.2021 No. 224 On Approval of the Requirements for the Welfare of Farmed Animals During Their Keeping
Preparation and approval of a regulatory document for the implementation of Commission Recommendation (EU) 2016/336 of 8 March 2016 on the application of Council Directive 2008/120/EC laying down minimum standards for the protection of pigs as regards measures to reduce the need for tail docking | bar: 2025 1 Jan. to 2026 12 Dec.
Activities to implement the EU farm animals welfare requirements during transport into Ukrainian national legislation
Preparation and approval of a regulatory document for the implementation of Council Regulation (EC) 1/2005 of 22 December 2004 on the protection of animals during transport and related operations
Regulation (EC) 1255/97 of 25 June 1997 on Community criteria for staging points and amending the route plan referred to in the Annex to Directive 91/628/EEC
Preparation and approval of a regulatory legal document for the implementation of Commission Delegated Regulation (EU) 2023/842 of 17 February 2023 supplementing Regulation (EU) 2017/625 of the European Parliament and of the Council as regards rules on official controls to verify compliance with animal welfare requirements during the transport of animals by livestock vessels
Preparation and approval of a regulatory legal document for the implementation of Commission Implementing Regulation (EU) 2023/372 of 17 February 2023 laying down rules on the recording, storage and exchange of written documents of official controls performed on livestock vessels, on contingency plans for livestock vessels in the event of emergencies, on the approval of livestock vessels and on minimum requirements applicable to exit points
Activities to implement the EU farm animals welfare requirements during killing into Ukrainian national legislation
Amendments to the Order of the Ministry of Agrarian Policy and Food of Ukraine dated October 11, 2018 No. 628, which approved the Requirements for ensuring the welfare of animals during killing and slaughter

## implementation of requirements
| Activity | Goal | Description of the approach for implementing the activity | Need for financial resources (yes/no, if yes, indicate source) | Responsible Government Authorities | Stakeholders involved | Deadline | Execution status (yellow - in progress, green - completed)
General activities to promote the implementation of requirements for the welfare of farm animals during keeping, transport and killing
| Conduct information campaigns to raise awareness about the welfare of farmed animals during keeping, transport and killing | There is a need to raise awareness of all target audiences regarding the requirements of national legislation for the welfare of farmed animals during keeping, transport and killing, as well as about the approaches to the practical implementation of these requirements; as well as consumers' asks for better welfare of farmed animals. | This activity will be implemented in accordance with the developed Information Campaign Plan (Annex 1 to Roadmap) on the welfare of farmed animals during keeping, transport and killing in Ukraine for 2025-2027, which includes target audiences, types of activities, approaches for the implementation. The indicators for verifying the effectiveness of the information campaign and the frequency of indicators evaluation will be described. | Yes (attracting resources from ITA Projects and other organisations) | Ministry of Economy/SSUFSCP | ITA projects, professional associations/business associations and other organisations (the list of stakeholders involved is in the description to the Information Campaign Plan) | According to the Information Campaign Plan (Annex 1) | Implementation of activities according to the information campaign plan is ongoing.
| Analyse the state of implementation of farm animal welfare requirements by business operators by sector | There is a need to understan how well business operators implement farm animal welfare requirements by sector in order to identify the main challenges faced by business operators, as well as which sectors and areas of activity primarily require support | The SSUFSCP will conduct an evaluation of the implementation of animal welfare legislation requirements by business operators by sector. After the initial data collection, an analysis will be carried out and conclusions prepared for each sector. | No | SSUFSCP | - | June 2026 | Wiil started after 1st of January 2026
| Implement the State targeted economic program for the Development of Livestock until 2033 | Stimulating investments into livestock enterprises in order to help them implement farm animals welfare requirements | The Ministry of Economy is implementing the program | State budget | Ministry of Economy | - | December 2033 | Implementation of program has been started in 2025
Activities to promote the implementation of animal welfare requirements during keeping
Ruminants | Preparation of guidelines for the practical implementation of requirements for the welfare of cattle and calves during keeping | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of cattle (calves, dairy cows, beef cattle) during their keeping. These guidelines are meant to help business operators simplify the process of reconstruction or construction of new facilities for keeping of farm animals in compliance with the new legislation, as well as avoid unnecessary costs and increase their awareness about the requirements. | - Conduct a comprehensive analysis of current Ukrainian legislation, as well as national standards and regulations of the EU countries that regulate the keeping conditions of cattle and calves. - Study the specifics of the work of business operators, in particular their needs and challenges related to the reconstruction or construction of new facilities. - Prepare detailed guidelines that will help business operators easily implement reconstruction or construction, avoid unnecessary costs when choosing a location and materials, and ensure compliance with the requirements for the construction of calf, walking areas, animal premises, etc. Include in the recommendations examples of best practices, ready-made design solutions and instructions that will reduce the time and resources required to implement welfare rules. | No | - | AVM, EFU | December 2025 | The experience of national guidelines of other countries has been studied. The preparation of draft guidelines is underway, which is scheduled to be presented for consultation with all involved organizations in November 2025
| Prepare guidelines for the practical implementation of requirements for the welfare of small cattle (sheep and goats) during keeping | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of small cattle (sheep and goats) during their keeping. These guidelines are meant to help business operators simplify the process of reconstruction or construction of new facilities for keeping of farm animals in compliance with the new legislation, as well as avoid unnecessary costs and increase their awareness about the requirements. | - Conduct a comprehensive analysis of current Ukrainian legislation, as well as national standards and regulations of the EU countries that regulate the keeping conditions of sheep and goats. - Study the specifics of the work of business operators, in particular their needs and challenges related to the reconstruction or construction of new facilities. - Prepare detailed guidelines that will help business operators easily implement reconstruction or construction, avoid unnecessary costs when choosing a location and materials, and ensure compliance with the requirements for the construction of animal premises, etc. Include in the recommendations examples of best practices, ready-made design solutions and instructions that will reduce the time and resources required to implement welfare rules. | No | - | GS VKU, Project 1882 / EfA, EFU | December 2025 | Draft guidelines have been prepared in accordance with EU recommendations. The next stage will be discussion with all stakeholders and their approval.
Broilers | Preparstion of guidelines for the practical implementation of requirements for the broiler welfare during keeping | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of broilers during their keeping. These guidelines are meant to help business operators simplify the process of reconstruction or construction of new facilities for keeping of farm animals in compliance with the new legislation, as well as avoid unnecessary costs and increase their awareness about the requirements. | - Conduct a comprehensive analysis of current Ukrainian legislation, as well as national standards and regulations of the EU countries that regulate the keeping conditions of broilers. - Study the specifics of the work of business operators, in particular their needs and challenges related to the reconstruction or construction of new facilities. - Prepare detailed guidelines that will help business operators easily implement reconstruction or construction, avoid unnecessary costs when choosing a location and materials, and ensure compliance with the requirements for the construction of animal premises, etc. Include in the recommendations examples of best practices, ready-made design solutions and instructions that will reduce the time and resources required to implement welfare rules. | No | - | Project 1882 / EfA, EFU | December 2025 | The drafting of guidelines has been started
Laying hens | Preparation of guidelines for the practical implementation of requirements for the welfare of laying hens during keeping | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of laying hens during their keeping. These guidelines are meant to help business operators simplify the process of reconstruction or construction of new facilities for keeping of farm animals in compliance with the new legislation, as well as avoid unnecessary costs and increase their awareness about the requirements. | - Conduct a comprehensive analysis of current Ukrainian legislation, as well as national standards and regulations of the EU countries that regulate the keeping conditions of laying hens. - Study the specifics of the work of business operators, in particular their needs and challenges related to the reconstruction or construction of new facilities. - Prepare detailed guidelines that will help business operators easily implement reconstruction or construction, avoid unnecessary costs when choosing a location and materials, and ensure compliance with the requirements for the construction of animal premises, etc. Include in the recommendations examples of best practices, ready-made design solutions and instructions that will reduce the time and resources required to implement welfare rules. | No | - | Project 1882 / EfA, EFU | December 2025 | The drafting of guidelines has been started
Pigs | Preparation of guidelines for the practical implementation of requirements for the welfare of pigs during keeping | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of pigs during their keeping. These guidelines are meant to help business operators simplify the process of reconstruction or construction of new facilities for keeping of farm animals in compliance with the new legislation, as well as avoid unnecessary costs and increase their awareness about the requirements. | - Conduct a comprehensive analysis of current Ukrainian legislation, as well as national standards and regulations of the EU countries that regulate the keeping conditions of pigs. - Study the specifics of the work of business operators, in particular their needs and challenges related to the reconstruction or construction of new facilities. - Prepare detailed guidelines that will help business operators easily implement reconstruction or construction, avoid unnecessary costs when choosing a location and materials, and ensure compliance with the requirements for the construction of animal premises, etc. Include in the recommendations examples of best practices, ready-made design solutions and instructions that will reduce the time and resources required to implement welfare rules. | No | - | ASU, SULAWE, Project 1882 / EfA, EFU | December 2025 | The drafting of guidelines has been started
Horses | Preparation of guidelines for the practical implementation of welfare requirements for working animals of the Equide family during keeping | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of working animals of the Equidae family during their keeping. | - Conduct a comprehensive analysis of current Ukrainian legislation, as well as national standards and regulations of the EU countries that regulate the keeping conditions of working animals of the Equidae family. - Prepare detailed guidelines that will help business operators easily implement reconstruction or construction, avoid unnecessary costs when choosing a location and materials, and ensure compliance with the requirements for the construction of animal premises, etc. Include in the recommendations examples of best practices, ready-made design solutions and instructions that will reduce the time and resources required to implement welfare rules. | No | - | Project 1882 / EfA, EFU | December 2026 | Not started
Other types of farm animals | Preparation of guidelines for the practical implementation of welfare requirements for lagomorphs and other farm animals during keeping | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of lagomorphs and other farm animals during their keeping. | - Conduct a comprehensive analysis of current Ukrainian legislation, as well as national standards and regulations of the EU countries that regulate the keeping conditions of lagomorphs and other farm animals. - Study the specifics of the work of business operators, in particular their needs and challenges related to the reconstruction or construction of new facilities. - Prepare detailed guidelines that will help business operators easily implement reconstruction or construction, avoid unnecessary costs when choosing a location and materials, and ensure compliance with the requirements for the construction of animal premises, etc. Include in the recommendations examples of best practices, ready-made design solutions and instructions that will reduce the time and resources required to implement welfare rules. | No | - | Project 1882 / EfA, EFU | December 2026 | Not started
Activities to promote the implementation of animal welfare requirements during transport
Control points | Promote the need to create control posts that are necessary for long-term animal transport among business operators | Compliance with national legislation on animal welfare during transport, which implements EU requirements, in particular the requirements of Regulation (EC) No 1255/97 of 25 June 1997 on Community criteria for staging points and amending the route plan referred to in the Annex to Directive 91/628/EEC | Hold a meeting with relevant associations and business associations to clarify the need to create control points that are necessary for long-term animal transport and the requirements of national legislation for such control point. Assist interested business operators in the creation and approval of control points. | No | SSUFSCP | `- | December 2026 | The first meeting with business operators and possible investors has been conducted to discuss the needenes of creation control posts in Ukraine and present the requirements to this posts. More meetings are planned.
Ruminants | Preparation of guidelines on the welfare of ruminants during transport | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of ruminants (calves, dairy cows, beef cattle, goats, sheeps) during their transport. | Prepare detailed guidelines to help transporters adapt their vehicles, including examples of best practices needed to implement welfare rules. | No | - | AVM, EFU | December 2026 | The drafting of guidelines has been started
Poultry | Preparation of guidelines for the welfare of poultry during transport | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of poultry during their transport. | Prepare detailed guidelines to help transporters adapt their vehicles, including examples of best practices needed to implement welfare rules. | No | - | Project 1882 / EfA (other organisation will be determined) | December 2026 | Not started
Pigs | Preparation of guidelines for the welfare of pigs during transport | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of pigs during their transport. | Prepare detailed guidelines to help transporters adapt their vehicles, including examples of best practices needed to implement welfare rules. | No | - | SULAWE, ASU, EFU | December 2026 | Not started
Horses | Preparation of guidelines for the welfare of horses during transport | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of horses during their transport. | Prepare detailed guidelines to help transporters adapt their vehicles, including examples of best practices needed to implement welfare rules. | No | - | Project 1882 / EfA, EFU (other organisation will be determined) | December 2026 | Not started
Activities to promote the implementation of animal welfare requirements at the time of killing
Ruminants | Preparation of guidelines for the welfare of ruminants during killing and related operations | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of ruminants during killing and related operations. | - Study the specifics of the work of business operators in particular their needs and challenges related to the reconstruction or construction of new facilities. - Prepare detailed guidelines that will help business operators easily implement reconstruction or construction, avoid unnecessary costs when choosing a location and materials, and ensure compliance with the requirements for the construction of animal premises, etc. Include in the recommendations examples of best practices, ready-made design solutions and instructions that will reduce the time and resources required to implement welfare rules. | No | - | AMU, EFU (other organisations will be determined) | December 2026 | Not started
Poultry | Preparation of guidelines for the welfare of poultry during killing and related operations | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of poultry during killing and related operations. | - Study the specifics of the work of business operators in particular their needs and challenges related to the reconstruction or construction of new facilities. - Prepare detailed guidelines that will help business operators easily implement reconstruction or construction, avoid unnecessary costs when choosing a location and materials, and ensure compliance with the requirements for the construction of animal premises, etc. Include in the recommendations examples of best practices, ready-made design solutions and instructions that will reduce the time and resources required to implement welfare rules. | No | - | Project 1882 / EfA, EFU (other organisations will be defined) | December 2026 | Not started
Pigs | Preparation of guidelines on the welfare of pigs during killing and related operations | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of pigs during killing and related operations. | - Study the specifics of the work of business operators in particular their needs and challenges related to the reconstruction or construction of new facilities. - Prepare detailed guidelines that will help business operators easily implement reconstruction or construction, avoid unnecessary costs when choosing a location and materials, and ensure compliance with the requirements for the construction of animal premises, etc. Include in the recommendations examples of best practices, ready-made design solutions and instructions that will reduce the time and resources required to implement welfare rules. | No | - | SULAWE, ASU, Project 1882 / EfA, EFU | December 2026 | Not started
Lagomorphs | Preparation of guidelines for the welfare of lagomorphs during killing and related operations | There is a need to create guidelines for the business operators regarding the practical implementation of national legislation of the welfare of lagomorphs during killing and related operations. | - Study the specifics of the work of business operators in particular their needs and challenges related to the reconstruction or construction of new facilities. - Prepare detailed guidelines that will help business operators easily implement reconstruction or construction, avoid unnecessary costs when choosing a location and materials, and ensure compliance with the requirements for the construction of animal premises, etc. Include in the recommendations examples of best practices, ready-made design solutions and instructions that will reduce the time and resources required to implement welfare rules. | No | - | Project 1882 / EfA, EFU (other organisations will be determined) | December 2027 | Not started

## implementation-calendar
Activity |  | 2025 | [11 empty] | 2026 | [11 empty] | 2027
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Jan. | Feb. | March | Apr. | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | March | Apr. | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | March | Apr. | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec.
General activities to promote the implementation of requirements for the welfare of farm animals during keeping, transport and slaughter
Conduct information campaigns to raise awareness about the welfare of farm animals during keeping, transport and slaughter
Analyse the state of implementation of farm animal welfare requirements by market operators by sector | bar: 2026 1 Jan. to 2026 6 June
Implement the State targeted economic program for the Development of Livestock until 2033 | bar: 2025 9 Sep. to 2027 12 Dec.
Activities to promote the implementation of animal welfare requirements during their keeping
Ruminants | Preparation of guidelines for the practical implementation of requirements for the welfare of cattle and calves during keeping | bar: 2025 8 Aug. to 2025 12 Dec.
Preparation of guidelines for the practical implementation of requirements for the welfare of small cattle (sheep and goats) during keeping | bar: 2025 8 Aug. to 2025 12 Dec.
Broilers | Preparation of guidelines for the practical implementation of requirements for the broiler welfare during keeping | bar: 2025 8 Aug. to 2025 12 Dec.
Laying hens | Preparation of guidelines for the practical implementation of requirements for the welfare of laying hens during keeping | bar: 2025 8 Aug. to 2025 12 Dec.
Pigs | Preparation of guidelines for the practical implementation of requirements for the welfare of pigs during keeping | bar: 2025 8 Aug. to 2025 12 Dec.
Horses | Preparation of guidelines for the practical implementation of welfare requirements for working animals of the Equide family during keeping | bar: 2026 1 Jan. to 2026 12 Dec.
Other types of farm animals | Preparation of guidelines for the practical implementation of welfare requirements for lagomorphs and other farm animals during keeping | bar: 2026 1 Jan. to 2026 12 Dec.
Activities to promote the implementation of animal welfare requirements during transport
Promote the need to create control points that are necessary for long-term animal transport among market operators | bar: 2025 11 Nov. to 2026 12 Dec.
Ruminants | Preparation of guidelines on the welfare of ruminants during transport | bar: 2026 4 Apr. to 2026 12 Dec.
Poultry | Preparation of guidelines for the welfare of poultry during transport | bar: 2026 4 Apr. to 2026 12 Dec.
Pigs | Preparation of guidelines for the welfare of pigs during transport | bar: 2026 4 Apr. to 2026 12 Dec.
Horses | Preparation of guidelines for the welfare of horses during transport | bar: 2026 4 Apr. to 2026 12 Dec.
Activities to promote the implementation of animal welfare requirements at the time of slaughter
Ruminants | Preparation of guidelines for the welfare of ruminants during slaughter and related operations | bar: 2026 1 Jan. to 2026 12 Dec.
Poultry | Preparation of guidelines for the welfare of poultry during slaughter and related operations | bar: 2026 1 Jan. to 2026 12 Dec.
Pigs | Preparation of guidelines on the welfare of pigs during slaughter and related operations | bar: 2026 1 Jan. to 2026 12 Dec.
Lagomorphs | Preparation of guidelines for the welfare of lagomorphs during slaughter and related operations | bar: 2027 1 Jan. to 2027 12 Dec.

## SSUFSCP`s tasks
| Activity | Goal | Description of the approach for implementing the activity | Need for financial resources (yes/no, if yes, indicate source) | Responsible Government Authorities | Stakeholders involved | Deadline | Execution status (yellow - in progress, green - completed)
General activities for the creation and implementation of a system of official control over compliance with farmed animal welfare requirements
| Study visit of representatives of the Ministry of Agrarian Policy and Food (currently Ministry of Economy) and the SSUFSCP to an EU Member official (the Netherlands) | Study of the experience of an EU Member official in implementing farmed animal welfare requirements and control measures to monitor compliance with these requirements | Study visit to the Netherlands was organised for representatives of the Ministry of Agrarian Policy and Food and the SSUFSCP. The list of participants was agreed with the management of the relevant organisations. After the study visit, the participants shared their experience with their colleagues during awareness-raising activities and are expected to implement the acquired experience during the implementation of EU requirements into national legislation, as well as durign the development and implementation of a system of official control over compliance with animal welfare legislation. | Yes (attracting resources from ITA projects and other organisations) | Ministry of Agrarian Policy and Food/SSUFSCP | EKNU/QFTP | April 7-11, 2025 | The study visit to the Netherlands took place from 7 to 11 April 2025 with the support of the Government of the Kingdom of the Netherlands and QFTP. The main purpose of the study visit was to study the experience of EU countries in implementing animal welfare requirements and carrying out official control measures to ensure compliance with these requirements. The visit was attended by 5 representatives of the Ministry of of Agrarian Policy and Food and the SSUFSCP. The participants of the study visit have already started to share the knowledge and experience gained with colleagues during the events and use them during the harmonization and implementation of national legislation on animal welfare. (https://qftp.org/navchalnyj-vizyt-do-niderlandiv-ukrainski-fakhivtsi-vyvchaly-pidkhody-u-vprovadzhenni-vymoh-ies-do-blahopoluchchia-silskohospodarskykh-tvaryn/).
| Study visit of representatives of the Ministry of Economy and the SSUFSCP to an EU Member official (the Netherlands, focus on ruminants) | Study of the experience of an EU member official in implementing farmed animal welfare requirements and control measures to monitor compliance with these requirements | Study visit to the Netherlands will be organised for representatives of the Ministry of Economy and the official Service for Food and Consumer Protction. The list of participants will be agreed with the management of the relevant organisations. After the study visit, the participants will share their experience with their colleagues during awareness-raising activities and will use the acquired experience during the implementation of EU requirements into national legislation, as well as during the development and implementation of a system of official control over compliance with animal welfare legislation. | Yes (attracting resources from ITA projects and other organisations) | Ministry of Economy/SSUFSCP | EKNU/QFTP | November 2025 | Preparation of the program and organisation of the study visit are ongoing (planned dates are 24-28 of November)
| Training of trainers (specialists at the central and regional levels of the SSUFSCP) on official control over compliance with the requirements of legislation on the welfare of farmed animals during keeping, transportation and killing | Training of 16 national trainers from the central and regional levels of the official Service for Food and Consumer Protection, of which: 8 trainers - on the issue of control during keeping; 2 trainers - on the issue of control over transport; 4 trainers - on the issue of control during killing; 2 trainers - on the issue of control at the border. | Trainings for trainers will be conducted with the involvement of national and international experts in accordance with the training program developed and approved by the SSUFSCP, which will include theoretical and practical training for trainers on issues of monitoring compliance with animal welfare legislation during the keeping, transport and killing of animals. | Yes (involvement of resources and experts from ITA projects) | SSUFSCP | QFTP, (additional organisations to be determined) | Training of trainers on the following issues: keeping - October 2025; killing - November 2025; transport - April 2026; borders - June 2026 | Training of trainers has been conducted from 20 till 24 of October 2025 (https://qftp.org/news/za-pidtrymky-qftp-dlya-fahivcziv-derzhprodspozhyvsluzhby-vidbuvsya-trening-shhodo-blagopoluchchya-silskogospodarskyh-tvaryn/)
| Conduct trainings for SSUFSCP specialists at the regional and local levels regarding official control over compliance with the requirements of legislation on the welfare of farmed animals during keeping, transport and killing | Conduct trainings by trained national trainers for SSUFSCP specialists at the regional and local levels to ensure a unified approach to official control over compliance by business operators with the requirements of legislation on the welfare of farmed animals during keeping, transport and killing throughout the country | This activity will be implemented in accordance with the developed training concept (annex 2) | Yes (involvement of resources and experts from ITA projects) | SSUFSCP | QFTP, (additional organisations to be determined) | April 2025-June 2027 (according to the training concept in annex 2) | The implementation of the training concept has started. To conduct the first training within the framework of the concept, a special short-term advanced training program “Animal Welfare Requirements and Official Control over Compliance with These Requirements (Basic Level)” was developed and approved, and online training was conducted from April 22 to 25, 2025. The purpose of this training was to increase the level of professional knowledge and competencies necessary to ensure a unified approach to official control over compliance by business operators with the requirements of national legislation on the welfare of farmed animals during keeping, transport and killing. 149 participants were registered to participate in the training, 148 of whom passed the final testing and received certificates (https://qftp.org/fakhivtsi-derzhprodspozhyvsluzhby-projshly-navchannia-shchodo-vymoh-do-blahopoluchchia-silskohospodarskykh-tvaryn/)
| Creation of a official Register of documents issued in accordance with animal welfare legislation | Fulfillment of the requirements of the Resolution of the Cabinet of Ministers No. 1520 | Development of technical specifications, selection of the developer for the Registry, direct development of the Registry and its testing | Yes (attracting resources from ITA projects and other organisations) | SSUFSCP | To be determined | creation of the Registry - December 2025; creation of the IT system - December 2026 | Not started
| Preparation of SOPs for maintaining the Register of documents issued in accordance with animal welfare legislation and the performance of its administrator functions | Providing SSUFSCP specialists with an algorithm of actions regarding 1) maintaining the Register; 2) the process of issuing, refusing to issue and canceling documents; 4) the process of providing extracts from the Register; 5) etc. | Preparation of draft SOP and submission for approval | No | SSUFSCP | To be determined | December 2026 | Not started
Activities for the implementation of official control measures for compliance with animal welfare requirements during their keeping
Ruminants | Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation when keeping ruminants (including calves) | Preparation of a tool that will contribute to a harmonised approach to inspections across the country, as it will contain an algorithm of actions for conducting inspections and will explain in more detail to the inspector what exactly and how to check in order to obtain confirmation for each question from the list of questions for inspection | Preparation of draft SOP and submission for approval | No | SSUFSCP | QFTP | December 2025 | First draft has been prepared and submitted to SSUFSCP for revision
Poultry | Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation when keeping broilers | Preparation of a tool that will contribute to a harmonised approach to inspections across the country, as it will contain an algorithm of actions for conducting inspections and will explain in more detail to the inspector what exactly and how to check in order to obtain confirmation for each question from the list of questions for inspection | Preparation of draft SOP and submission for approval | No | SSUFSCP | To be determined | March 2026 | Not started
| Prepare SOPs for determining broiler stocking density and the procedure for approving its increase | Preparation of a tool that will facilitate a harmonized approach to determining broiler stocking density on poultry farms across the country and explain in more detail the procedure for approving an increase in density | Preparation of draft SOP and submission for approval | No | SSUFSCP | To be determined | June 2026 | Not started
| Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation when keeping laying hens | Preparation of a tool that will contribute to a harmonized approach to inspections across the country, as it will contain an algorithm of actions for conducting inspections and will explain in more detail to the inspector what exactly and how to check in order to obtain confirmation for each question from the list of questions for inspection | Preparation of draft SOP and submission for approval | No | SSUFSCP | ILCA II | December 2025 | First draft has been prepared and submitted to SSUFSCP for revision
Pigs | Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation when keeping pigs | Preparation of a tool that will contribute to a harmonized approach to inspections across the country, as it will contain an algorithm of actions for conducting inspections and will explain in more detail to the inspector what exactly and how to check in order to obtain confirmation for each question from the list of questions for inspection | Preparation of draft SOP and submission for approval | No | SSUFSCP | Project 1882 / EfA, SULAWE, additional organizations to be identified | March 2026 | Not started
Horses | Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation when keeping working animals belonging to the Equide family | Preparation of a tool that will contribute to a harmonized approach to inspections across the country, as it will contain an algorithm of actions for conducting inspections and will explain in more detail to the inspector what exactly and how to check in order to obtain confirmation for each question from the list of questions for inspection | Preparation of draft SOP and submission for approval | No | SSUFSCP | Project 1882 / EfA, additional organizations to be identified | December 2026 | Not started
Activities to implement official control measures for compliance with animal welfare requirements during transport
General activities | Participation of SSUFSCP representatives in the fifth meeting of the regional network of national contact points of the World Organisation for Animal Health (WOAH) on long-distance animal transport in Europe | Understanding approaches to implementing EU requirements and WOAH standards for the welfare of farm animals during long-distance transport and implementing measures to monitor compliance with these requirements | Representatives of the SSUFSCP will participate in this event and transfer the acquired knowledge to their colleagues during awareness-raising activities and will use the acquired experience during the development and implementation of a system of official control over compliance with the requirements of legislation on animal welfare during transport. | Yes (WOAH) | SSUFSCP | `- | March 10-13, 2025 | One representative of the SSUFSCP participated in the fifth meeting of the regional network of national contact points of the World Organisation for Animal Health (WOAH) on long-distance animal transport in Europe
| Study the experience of EU Member officials in implementing animal welfare requirements during transport and implementing measures to monitor compliance with these requirements | Understanding of the practical aspects of implementing EU requirements, in particular Council Regulation (EC) 1/2005, Regulation (EC) 1255/97, Commission Delegated Regulation (EU) 2023/842 and Commission Implementing Regulation (EU) 2023/372 | Available information on the implementation of animal welfare requirements during transport and the implementation of control measures for compliance with these requirements in the EU Member officials will be collected and analysed, a report will be prepared and sent to the specialists of the Ministry of Agriculture and the SSUFSCP. After they have processed the report, a meeting will be held in the form of an expert discussion with the involvement of representatives of the EC and EU Member officials. | No | SSUFSCP | QFTP | June 2025 | In order to study the experience of EU Member officials in implementing requirements for the welfare of farm animals during transportation and implementing control measures for compliance with these requirements, available information was collected and analyzed for 5 EU Member officials (the Republic of Slovenia, the Republic of Croatia, the Kingdom of Spain, the Republic of Finland and the Netherlands) and a report was prepared. The report was sent to the Ministry of Economy and the official Service for Food and Consumer Protection on June 30, 2025. The materials of the report were also presented during an online training for specialists of the official Service for Food and Consumer Protection on the topic "Animal welfare requirements and official control (inspection) over compliance with these requirements (basic level)", which took place on April 22-25, 2025.
| Participation of SSUFSCP representatives in BTSF training on animal welfare during transport | Understand approaches to implementing EU requirements for the welfare of farm animals during transport and implementing measures to monitor compliance with these requirements | Representatives of the SSUFSCP will participate in this event and transfer the acquired knowledge to their colleagues during awareness-raising activities and will implement the acquired experience during the development and implementation of a system of official control over compliance with the requirements of legislation on animal welfare during transport. | Yes (BTSF) | SSUFSCP | - | June-September 2025 | 2 SSUFSCP specialists participated in the BTSF training, which took place in June 2025 in Budapest, Hungary; 1 QFTP expert participated in the BTSF held in Plovdiv, Bulgaria in September 2025. These participants will transfer the acquired knowledge during local training events on the topic of animal welfare during transport.
| Create a register of transporters, drivers, vehicles for transporting animals, issued permits for long-distance transport | Compliance with national legislation on animal welfare during transport, which implements EU requirements, in particular the requirements of Council Regulation (EC) 1/2005 | Development of technical specifications, selection of the registry developer, direct development of the registry and its testing | Yes (attracting resources from ITA projects and other organisations) | SSUFSCP | To be determined | December 2026 | Not started
| Prepare SOPs for registration of transporters, drivers, vehicles for transporting animals, issued permits for long-distance transport and maintenance of such a register | Providing SSUFSCP specialists with an algorithm of actions for registering transporters, drivers, vehicles for transporting animals, issued permits for long-term transport, and maintaining such a register | Preparation of draft SOP and submission for approval | No | SSUFSCP | To be determined | December 2026 | Not started
| Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by registered transporters of farm animals with the requirements of animal welfare legislation | Preparation of a tool that will contribute to a harmonized approach to inspections across the country, as it will contain an algorithm of actions for conducting inspections and will explain in more detail to the inspector what exactly and how to check in order to obtain confirmation for each question from the list of questions for inspection | Preparation of draft SOP and submission for approval | No | SSUFSCP | To be determined | December 2026 | Not started
| Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation during transport | Preparation of a tool that will contribute to a harmonized approach to inspections across the country, as it will contain an algorithm of actions for conducting inspections and will explain in more detail to the inspector what exactly and how to check in order to obtain confirmation for each question from the list of questions for inspection | Preparation of draft SOP and submission for approval | No | SSUFSCP | To be determined | December 2026 | Not started
| Prepare SOPs for carrying out official control (inspection) of an approved control point required for animals to rest during long-term transport | Preparation of a tool that will contribute to a harmonized approach to inspections across the country, as it will contain an algorithm of actions for conducting inspections and will explain in more detail to the inspector what exactly and how to check in order to obtain confirmation for each question from the list of questions for inspection | Preparation of draft SOP and submission for approval | No | SSUFSCP | To be determined | December 2026 | Not started
| Prepare SOPs for official control of animal transporters at border inspection posts regarding their compliance with the requirements of legislation on animal welfare during transport | Preparation of a tool that will contribute to a harmonized approach to official control throughout the country, as it will contain an algorithm of actions for official control and will explain to the inspector in more detail what exactly needs to be checked and how | Preparation of draft SOP and submission for approval | No | SSUFSCP | To be determined | December 2026 | Not started
| Create a register of transporters of live animals for the transport by vessels and approval of such vessels | Compliance with national legislation on animal welfare during transport, which implements EU requirements, in particular the requirements of Council Regulation (EC) 1/2005, Commission Delegated Regulation (EU) 2023/842 and Commission Implementing Regulation (EU) 2023/372 | Development of technical specifications, selection of the developer of the Registry, direct development of the Registry and its testing | Yes (attracting resources from ITSP projects and other organizations) | SSUFSCP | To be determined | December 2026 | Not started
| Preparation of SOPs on the register of carriers of live animals transported by vessels, approval of vessels for the transport of animals and maintenance of such a register | Providing SSUFSCP specialists with an algorithm of actions for registering transporters of live animals transported by vessels and approving such vessels | Preparation of draft SOP and submission for approval | No | SSUFSCP | To be determined | June 2027 | Not started
Activities to implement official control measures for compliance with animal welfare requirements during killing
Ruminants | Підготовка СОП щодо державного контролю за дотриманням оператором потужності, що здійснює забій, законодавства про благополуччя тварин під час забою та умертвіння жуйних тварин (для офіційного ветеринарного лікаря) | Preparation of a tool that will contribute to a harmonized approach to inspections across the country, as it will contain an algorithm of actions for official veterinarian | Preparation of draft SOP and submission for approval | No | SSUFSCP | QFTP | December 2025 | The draft SOP for the official veterinarian was developed and sent on 30.06.2025 to the SSUFSCP for consideration and further approval
| Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation during killing of ruminants | Preparation of a tool that will contribute to a harmonized approach to inspections across the country, as it will contain an algorithm of actions for conducting inspections and will explain in more detail to the inspector what exactly and how to check in order to obtain confirmation for each question from the checklist for inspection | Preparation of draft SOP and submission for approval | No | SSUFSCP | QFTP | February 2025 | Preparation of the draft SOP for inspectors is underway.
Bird | Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation during the slaughter of broilers | Preparation of a tool that will contribute to a harmonized approach to inspections across the country, as it will contain an algorithm of actions for conducting inspections and will explain in more detail to the inspector what exactly and how to check in order to obtain confirmation for each question from the list of questions for inspection | Preparation of draft SOP and submission for approval | No | SSUFSCP | ILCA II | December 2025 | Preparation of the draft SOP is underway.
Pigs | Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation during the slaughter of pigs | Preparation of a tool that will contribute to a harmonized approach to inspections across the country, as it will contain an algorithm of actions for conducting inspections and will explain in more detail to the inspector what exactly and how to check in order to obtain confirmation for each question from the list of questions for inspection | Preparation of draft SOP and submission for approval | No | SSUFSCP | SULAWE, Project 1882 / EfA, additional organizations to be identified | February 2026 | Not started

## SSUFSCP`s tasks - calendar
Activity |  | 2025 | [11 empty] | 2026 | [11 empty] | 2027
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Jan. | Feb. | March | Apr. | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | March | Apr. | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | March | Apr. | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec.
General activities for the creation and implementation of a system of official control over compliance with farmed animal welfare requirements
Study visit of representatives of the Ministry of Agrarian Policy and Food (currently Ministry of Economy) and the SSUFSCP to an EU Member official (the Netherlands) | bar: 2025 4 Apr.
Study visit of representatives of the Ministry of Economy and the SSUFSCP to an EU Member official (the Netherlands, focus on cattle) | bar: 2025 11 Nov.
| Training of trainers (specialists at the central and regional levels of the SSUFSCP) on official control over compliance with the requirements of legislation on the welfare of farm animals during keeping, transportation and killing | 2025 10 Oct.: keeping; 2025 11 Nov.: killing; 2026 4 Apr.: transport; 2026 6 June: border control
Conduct trainings for SSUFSCP specialists at the regional and local levels regarding official control over compliance with the requirements of legislation on the welfare of farmed animals during keeping, transport and killing | bar: 2025 11 Nov. to 2027 6 June
Creation of a official Register of documents issued in accordance with animal welfare legislation | bar: 2025 9 Sep. to 2026 12 Dec.
Preparation of SOPs for maintaining the Register of documents issued in accordance with animal welfare legislation and the performance of its administrator functions | bar: 2026 1 Jan. to 2026 12 Dec.
Activities for the implementation of official control measures for compliance with animal welfare requirements during their keeping
Ruminants | Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation when keeping ruminants (including calves) | bar: 2025 7 July to 2025 12 Dec.
Poultry | Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation when keeping broilers | bar: 2025 11 Nov. to 2026 3 March
Prepare SOPs for determining broiler stocking density and the procedure for approving its increase | bar: 2026 1 Jan. to 2026 6 June
Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation when keeping laying hens | bar: 2025 3 March to 2025 12 Dec.
Pigs | Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation when keeping pigs | bar: 2025 11 Nov. to 2026 3 March
Horses | Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation when keeping working animals belonging to the Equide family | bar: 2026 4 Apr. to 2026 12 Dec.
Activities to implement official control measures for compliance with animal welfare requirements during transport
General activities | Participation of SSUFSCP representatives in the fifth meeting of the regional network of national contact points of the World Organisation for Animal Health (WOAH) on long-distance animal transport in Europe | bar: 2025 3 March
Study the experience of EU Member officials in implementing animal welfare requirements during transport and implementing measures to monitor compliance with these requirements | bar: 2025 6 June
Participation of SSUFSCP representatives in BTSF training on animal welfare during transport | bar: 2025 6 June; 2025 9 Sep.
Create a register of transporters, drivers, vehicles for transporting animals, issued permits for long-distance transport | bar: 2026 1 Jan. to 2026 12 Dec.
Prepare SOPs for registration of transporters, drivers, vehicles for transporting animals, issued permits for long-distance transport and maintenance of such a register | bar: 2026 1 Jan. to 2026 12 Dec.
Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by registered transporters of farm animals with the requirements of animal welfare legislation | bar: 2026 1 Jan. to 2026 12 Dec.
Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation during transport | bar: 2026 1 Jan. to 2026 12 Dec.
Prepare SOPs for carrying out official control (inspection) of an approved control point required for animals to rest during long-distance transport | bar: 2026 1 Jan. to 2026 12 Dec.
Prepare SOPs for official control of animal transporters at border inspection posts regarding their compliance with the requirements of legislation on animal welfare during transport | bar: 2026 1 Jan. to 2026 12 Dec.
Create a register of transporters of live animals for the transport by vessels and approval of such vessels | bar: 2026 1 Jan. to 2026 12 Dec.
Preparation of SOPs on the register of carriers of live animals transported by vessels, approval of vessels for the transport of animals and maintenance of such a register | bar: 2027 1 Jan. to 2027 6 June
Activities to implement official control measures for compliance with animal welfare requirements during slaughter
Ruminants | Preparation of SOPsfor the implementation of official control of compliance by the operator of the slaughtering facility with legislation on animal welfare during slaughter and killing of ruminants (for the official veterinarian) | bar: 2025 5 May to 2025 6 June
Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation during slaughter of ruminants | bar: 2025 12 Dec. to 2026 2 Feb.
Poultry | Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation during the slaughter of broilers | bar: 2025 9 Sep. to 2025 12 Dec.
Pigs | Prepare SOPs for the implementation of official control (inspection) measures regarding compliance by business operators with the requirements of animal welfare legislation during the slaughter of pigs | bar: 2025 9 Sep. to 2026 2 Feb.